## Sheet1
Task Schedule |  |  |  |  | Last Update
Deadline | Task | Who | Contribution Value | Status
2018-09-28 | Initial Group Meeting | Everyone |  | Complete
ongoing | Meeting Minutes 1 | Brendon |  | Complete
2018-10-01 | Look into Proposal Directions | Collin B/Taj |  | Complete
ongoing | Waste management Research | Collin E |  | Complete
Complete
Complete
2018-10-01 | Proposal Draft Due | Everyone |  | Complete
| Meeting Minutes 2 | Matt C |  | In Progress
2018-10-01 | Scribe Draft | Collin B |  | In Progress
2018-10-01 | Collaborate on Draft | Everyone |  | In Progress
In Progress
| Initial Research |  |  | In Progress
| Research Documentation |  |  | In Progress
2018-10-05 | Task Schedule Due | Everyone |  | In Progress
2018-10-05 | Group Meeting | Everyone |  | In Progress
2018-10-08 | Proposal Due | Everyone |  | In Progress
| Motivation Statement | Everyone |  | In Progress
| Proposal Intro | Matthew |  | In Progress
| Proposal Background | Collin B |  | In Progress
| Proposal Benefits | Taj |  | In Progress
Mahlek S
| Proposal Methods | Mahlek S |  | In Progress
| Proposal Schedule | Brendon |  | In Progress
| Proposal Conclusion | Collin E |  | In Progress
2018-10-09 | Compile and Submit Proposal | Matthew |  | In Progress
2018-10-12 | Research Ideas | Everyone |  | Incomplete
| Research Documentation | Everyone |  | Incomplete
2018-10-17 | Group Think in Doc | Everyone |  | Incomplete | MC
| Research Outline? |  |  | Incomplete
2018-10-19 | Group Meeting - Fri. 9:25AM | Everyone |  | Incomplete
| Research |  |  | Incomplete
| Research Documentation |  |  | Incomplete
2018-10-26 | Group Meeting | Everyone |  | Incomplete
| Progress Report write up |  |  | Incomplete
2018-10-31 | Progress Report Draft |  |  | Incomplete
2018-11-02 | Group Meeting | Everyone |  | Incomplete
Research
Research Documentation
Incomplete
2018-11-07 | Progress Report Due | Everyone |  | Incomplete
2018-11-09 | Group Meeting | Everyone |  | Incomplete
| Research |  |  | Incomplete
| Research Documentation |  |  | Incomplete
Technical report write up
Portfolio Write up
Incomplete
2018-11-16 | Group Meeting | Everyone |  | Incomplete
| Technical Report Draft |  |  | Incomplete
| Technical report revisions |  |  | Incomplete
2018-11-25 | Technical Report |  |  | Incomplete
| Portfolio Draft |  |  | Incomplete
2018-11-28 | Portfolio Draft Due | Everyone |  | Incomplete
Incomplete
2018-11-30 | Group Meeting | Everyone |  | Incomplete
| Portfolio Final Revisions |  |  | Incomplete
2018-12-05 | Portfolio Due | Everyone |  | Incomplete